## Cover Page
vSphere Shared Disk Cluster Migration
Document Information
Document Version: | 2.0
Date Updated: | September 19, 2026
Migration Type: | Cold cross-vCenter migration using Phase I Final v1.2.0 and Phase II Final v2.2.0
Configuration: | Virtual Machine with shared Multi-writer VMDKs; SCSI bus sharing: None
Primary Reference: | Broadcom KB 390585 and KB 313527
Environment Details
Source vCenter: | <SOURCE_VCENTER_FQDN>
Target vCenter: | <TARGET_VCENTER_FQDN>
Primary VM Name: | <PRIMARY_VM_NAME>
Secondary VM Name: | <SECONDARY_VM_NAME>
Target Cluster: | <TARGET_CLUSTER_NAME>
Target Storage: | <TARGET_DATASTORE_OR_DATASTORE_CLUSTER>
CRITICAL OPERATING MODEL
Primary VM: | All shared VMDKs remain attached during migration. If cross-vCenter migration removes Multi-writer, Phase II restores Multi-writer only to disks identified as shared in the Phase I manifest before Secondary reconstruction.
Secondary VM: | Only Secondary disks captured as Multi-writer in the Phase I manifest are detached. Virtual devices are removed without a file operation; backing VMDKs are never deleted.
Automation boundary: | Phase I discovers, validates, exports evidence, and performs controlled Secondary detach. Phase II verifies evidence, restores missing Primary Multi-writer, reattaches existing VMDKs to the Secondary, and validates. Neither utility migrates nor powers on VMs.

## Pre-Migration Checklist
Pre-Migration Checklist
✓ | Item | Status | Notes
Change Control and Ownership
Approved change record and maintenance window
Oracle DBA identifies active and standby nodes and approves shutdown/startup sequence
Cloud administrator, Oracle DBA, storage, network, backup, and change contacts are available
Rollback decision point and maximum outage duration are documented
Source Health and Protection
Confirm Oracle RAC, ASM, OCR, and voting-disk health before shutdown
Verify recent application-consistent backup and recovery plan
Confirm no VM snapshots exist on either node
Confirm CBT and backup workflows will not conflict with Multi-writer disks
Confirm both VMs can be cleanly shut down through the guest OS
Destination Readiness
Verify target vCenter, cluster, hosts, storage, and network inventory
Confirm destination capacity with project-approved headroom
Validate storage type, storage policy, disk format, and Multi-writer support for Oracle RAC; plan for Phase II to restore Multi-writer if cross-vCenter migration removes the flag
Do not assume Clustered VMDK support is required; validate the actual Multi-writer design for vSAN, VMFS, NFS, or vVols
Verify target port groups, VLANs, MTU, routing, and MAC-retention requirements
Verify cross-vCenter cold-migration connectivity, including applicable ESXi provisioning or NFC paths
Configuration Evidence
Capture the complete Phase I JSON manifest, checksum, validation files, and reviewable CSV inventory for both VMs
Record all disks, including private dependent disks and shared Independent-Persistent disks
Record controller type, bus number, bus-sharing mode, device key, unit number, and SCSI node
Correlate every shared disk by backing identity, not by Hard disk label or capacity alone
Record source datastore identity, VMDK path, storage policy, provisioning characteristics, and backing UUID/content ID when available
Verify no RDM or unsupported backing type exists unless covered by an approved separate procedure

## Phase 1 - Documentation
Phase 1: Source Discovery, Documentation, and Evidence Export
Task | Description / Command | Completed
1.1 | Launch vSphere_Shared_Disk_Cluster_Migration_Assistant_Phase_I_Final_v1.2.0.ps1 in PowerShell 7 STA and select an approved evidence output folder.
1.2 | Connect the Phase I assistant to the source vCenter using an approved account. Credentials remain in memory only; saved profiles do not include passwords.
1.3 | Enter the Primary/Active and Secondary/Standby VM names. Resolve exactly one inventory object for each role and confirm the objects are different.
1.4 | Discover and review both VM records, all SCSI controllers, every private disk, every shared disk, and all storage-policy and backing metadata.
1.5 | Correlate each Secondary Multi-writer disk to exactly one Primary disk by canonical backing identity or backing UUID and capacity. Never rely on the Hard disk label alone.
1.6 | Validate powered-off readiness, connection state, snapshots, consolidation, CBT, backing type, duplicate SCSI nodes, disk modes, and all shared-disk correlations. Any blocking finding prevents export or detach.
1.7 | Export SharedDiskMigrationManifest.json, the companion SHA-256 file, VM-Summary.csv, ControllerInventory.csv, DiskInventory.csv, SharedDiskCorrelation.csv, PreChange-Validation.json, PlannedChanges.json, and Export-Summary.json.
1.8 | Review the manifest and checksum with the cloud administrator and Oracle DBA. Preserve the entire run folder as the authoritative Phase I evidence package.
1.9 | Confirm the manifest lists only the Secondary devices that were Multi-writer in live source inventory and records FileOperation as None.
1.10 | Do not create VMware snapshots. Independent-persistent Multi-writer disks are governed by the application and the manifest/evidence package, not by a VM snapshot rollback.

## Oracle Shutdown
Database Controlled Shutdown
Step | DBA-Controlled Action | Completed
2.1 | DBA records pre-change cluster status, database status, ASM status, OCR status, voting-disk status, and node membership.
2.2 | DBA stops application traffic and confirms no new database workload is entering the cluster.
2.3 | DBA stops the secondary database instance and validates the primary remains stable. Use site-approvedDB commands for the installed version and configuration.
2.4 | DBA stops the primary database instance and confirms the database is fully stopped.
2.5 | DBA stops secondary node applications, ASM, andDB High Availability Services in the approved order.
2.6 | DBA stops primary node applications, ASM, andDB High Availability Services in the approved order.
2.7 | Verify noDB, ASM, CRS, or application processes retain access to shared storage.
2.8 | DBA issues a formal handoff: both nodes are quiesced and safe for guest operating-system shutdown.

## VM Shutdown and Detach
VM Shutdown and Phase I Controlled Detach
Step | Action / Validation | Completed
3.1 | Shut down the Secondary/Standby guest first using the approved operating-system procedure. Do not force power off unless approved.
3.2 | Shut down the Primary/Active guest second using the approved operating-system procedure.
3.3 | Verify both VMs report poweredOff in live source-vCenter inventory. Phase I blocks configuration changes if either VM is powered on.
3.4 | Refresh discovery and rerun source validation immediately before detach. Export a new manifest if ChangeVersion or hardware configuration changed.
3.5 | Select Preview Detach Contract. Review the exact Secondary device keys, VMDK paths, capacities, original SCSI nodes, disk modes, and sharing modes.
3.6 | Require typed confirmation: DETACH SHARED DISKS FROM <SECONDARY_VM_NAME>.
3.7 | Detach only Secondary devices captured as Multi-writer. Use one reconfiguration task, remove virtual devices only, keep FileOperation unset, and never delete VMDKs.
3.8 | Verify the Primary remains unchanged, all Primary shared VMDKs remain attached, and all Secondary private disks remain attached.
3.9 | Review AppliedChanges.json and PostChange-Validation.json. Proceed only when the application reports PASS: READY FOR COLD MIGRATION.
3.10 | Preserve the Phase I run folder and hand the manifest, checksum, applied-change evidence, and post-change validation to the migration and Phase II operators.

## Perform Migration
Phase 4: Cold Cross-vCenter Migration and Destination Hold Point
Step | Action / Validation | Completed
4.1 | Verify both source VMs remain powered off and Phase I reports READY FOR COLD MIGRATION.
4.2 | Reconfirm destination cluster, compatibility, networks, storage capacity, storage policy, and Multi-writer support.
4.3 | Reconfirm vCenter management connectivity and required ESXi provisioning or NFC paths.
4.4 | Cold-migrate the Primary VM first with all private and shared VMDKs attached.
4.5 | Do not power on the Primary VM at the destination.
4.6 | Verify the destination Primary exists, is powered off, and has all expected disks. Record the live destination VMDK paths and UUIDs.
4.7 | Do not assume cross-vCenter migration preserved Multi-writer. Phase II treats a missing flag on a manifest-identified Primary shared disk as a controlled preparation requirement.
4.8 | Cold-migrate the Secondary VM with private disks only.
4.9 | Do not power on the Secondary VM at the destination.
4.10 | Verify the Secondary retains its private disks and controller topology and has no shared disks attached.
4.11 | Do not use OVF export/import as an unplanned fallback. Stop, preserve evidence, diagnose the failure, and use an independently approved recovery method.

## Phase 5 - Disk Reattach
Phase 5: Phase II Destination Preparation, Reconstruction, and Validation
Step | Action / Validation | Completed
5.1 | Launch vSphere_Shared_Disk_Cluster_Migration_Assistant_Phase_II_Final_v2.2.0.ps1 and connect independently to the destination vCenter.
5.2 | Import SharedDiskMigrationManifest.json. Phase II locates the companion .sha256 or .sha256.txt file, verifies integrity, preserves dates as strings, and confirms successful Phase I validation and detach evidence.
5.3 | Resolve exactly one destination Primary and Secondary VM and verify both remain powered off.
5.4 | Discover destination controllers, private disks, shared disks, backing paths, UUIDs, capacities, disk modes, and sharing state.
5.5 | Map each Phase I shared disk to exactly one destination Primary backing using UUID plus capacity, with VMDK base name plus capacity as a controlled fallback. Ambiguous mapping is blocking.
5.6 | Validate Secondary private disks against the original SCSI nodes and capacities. Verify the original shared-disk target nodes are unoccupied before reconstruction.
5.7 | If a manifest-identified Primary shared disk is no longer Multi-writer, Phase II reports Primary preparation required instead of a terminal block.
5.8 | Select Prepare Destination Primary. Require typed confirmation, edit only the mapped Primary shared-disk devices, set sharingMultiWriter, preserve backing path, device key, controller, unit number, capacity, and disk mode, and keep FileOperation unset.
5.9 | Re-query the Primary. Continue only when every originally shared Primary disk reports Multi-writer and destination readiness reports Pass.
5.10 | Select Execute Destination Reconstruction and enter the displayed typed confirmation.
5.11 | Attach each existing destination VMDK to the Secondary using a unique temporary negative device key, the live Secondary controller key, the original unit number, independent_persistent, and sharingMultiWriter. Keep FileOperation unset.
5.12 | Re-query both VMs and validate one exact Primary and one exact Secondary match for each shared backing. Verify canonical paths, UUIDs, capacities, Multi-writer, Secondary disk mode, and original SCSI nodes.
5.13 | Review Destination-Reconstruction-Applied.json, Destination-Final-Validation.json, and Destination-Final-Mappings.csv. Proceed only when every FinalStateCompliant value is True and status is Pass.
5.14 | Leave both VMs powered off. The required final status is PASS: READY FOR CONTROLLED PRIMARY POWER-ON.

## Phase 6 - Power On
Phase 6: Controlled Power-On and Operating-System Validation
Step | Action / Validation | Completed
6.1 | Cloud administrator and Oracle DBA review the final comparison report and approve power-on. The migration assistant does not power on VMs.
6.2 | Cloud administrator powers on the Primary VM only.
6.3 | Verify primary console access, operating-system boot, VMware Tools status, expected NIC state, IP configuration, routes, DNS, and cluster-interconnect reachability.
6.4 | Oracle DBA verifies expected shared devices through approved non-destructive discovery methods such as lsblk, oracleasm listdisks, multipath -ll, or ASM discovery appropriate to the environment.
6.5 | Do not issue arbitrary raw-device writes. Any device-level read test must be explicitly approved by the DBA and performed only against a positively identified device.
6.6 | Review guest and ESXi logs for storage, reservation, lock, path, or I/O errors.
6.7 | Oracle DBA approves Secondary VM power-on after the Primary VM and shared storage pass validation.
6.8 | Cloud administrator powers on the Secondary VM.
6.9 | Verify secondary operating-system, network, VMware Tools, shared-device discovery, and absence of storage errors.
6.10 | Reconfirm both vCenter disk devices reference the same shared VMDKs and report Multi-writer.

## Phase 7 - Oracle Validation
Phase 7: Validation and Service Restoration
Step | DBA-Controlled Validation | Completed
7.1 | DBA starts and validates DB High Availability Services on the Primary node using site-approved commands.
7.2 | Validate ASM discovery and mount state on the Primary node.
7.3 | Validate OCR integrity and voting-disk status.
7.4 | Start and validate DBHigh Availability Services and ASM on the Secondary node.
7.5 | Validate cluster interconnect, node membership, VIPs, listeners, and cluster resources.
7.6 | Start the Primary database instance and validate OPEN status and application connectivity.
7.7 | Start the Secondary database instance and validate full RAC status.
7.8 | Perform DBA-approved functional and application validation. Do not create test database objects unless the change plan specifically authorizes them.
7.9 | Perform failover or service-relocation testing only when separately approved within the maintenance window.
7.10 | Restore application traffic, backup schedules, and monitoring after RAC and business-owner approval.
7.11 | Capture final cluster status, ASM status, database status, vCenter configuration report, and stakeholder sign-off.

## Configuration Docs
VM and Shared-Disk Configuration Record
Configuration Item | Primary VM | Secondary VM | Validation / Notes
VM Name
Role
Power State
VM MoRef
VM Instance UUID
VM Config UUID
Source Cluster / Host
Destination Cluster / Host
VM Folder / Resource Pool
vCPU / Memory
Hardware Version
Guest OS
SCSI Controller 0 Type / Bus Number / Bus Sharing
SCSI Controller 1 Type / Bus Number / Bus Sharing
Additional SCSI Controllers
Private Disk Count
Shared Multi-writer Disk Count
Shared Disk Source VMDK Path
Shared Disk Destination VMDK Path
Shared Disk Capacity Bytes
Shared Disk Original SCSI Node
Shared Disk Destination SCSI Node
Shared Disk Sharing Mode
Shared Disk Disk Mode
Shared Disk Storage Policy
Backing UUID / Content ID
Datastore Name / UUID
NIC / Port Group / MAC
Snapshots Present
CBT State
Manifest Comparison Result
Phase I Manifest ID / SHA-256
Phase I Detach Task / Result
Primary Multi-writer Preparation Task / Result
Secondary Reconstruction Task / Result
FinalStateCompliant / ReconstructionStatus

## Troubleshooting
Troubleshooting and Stop Conditions
Issue / Symptom | Safe Response | Escalation / Evidence
Cross-vCenter cold migration fails | Keep both VMs powered off. Preserve source configuration and evidence. Review task events, vCenter, ESXi connectivity, destination compatibility, capacity, DNS, time, and provisioning/NFC paths. Do not switch to OVF without separate approval. | Migration lead, virtualization platform owner, network team
Destination Primary shared disk is mapped but not Multi-writer | Expected recoverable condition. Keep both VMs powered off and use Phase II Prepare Destination Primary. The tool restores Multi-writer only to Phase I manifest-identified shared disks and validates the result. | Virtualization and storage teams; attach Phase I manifest and Primary preparation evidence
Destination shared-disk mapping is ambiguous | Stop. Do not attach a disk. Resolve using backing UUID, capacity, destination Primary attachment, canonical path, and approved operator evidence. | Migration lead and storage owner
Original SCSI unit number is occupied on Secondary before reconstruction | Stop. Do not auto-select another unit number. Reconcile destination controller and private-disk topology against the manifest. | Virtualization engineer and Oracle DBA
Phase II reports deviceChange[n].device.key | Use the finalized Phase II script. Every device added in one reconfiguration specification must use a unique temporary negative device key. Confirm no partial Secondary change occurred before retry. | Virtualization engineer; attach reconstruction request and exception artifact
Reconstruction confirmation reports an undeclared x prefix | Use the finalized Phase II script whose confirmation XAML declares the x namespace. No VM task is submitted when dialog parsing fails. | Tool owner
Connection profile property is missing | Use the finalized Phase II script. It supports DestinationVCenter/DestinationUsername and legacy SourceVCenter/SourceUsername profiles. Passwords are never loaded from a profile. | Tool owner
Secondary cannot power on or reports file lock | Power off both nodes if necessary. Verify both devices point to the same VMDK, Multi-writer is enabled on both, disk mode and storage support are valid, and no unsupported snapshot/CBT condition exists. | Virtualization and storage teams
Oracle ASM, OCR, or voting disk not discovered | Keep database services stopped. Validate guest discovery, WWIDs, udev/ASM rules, multipath state, SCSI addresses, and shared-VMDK mapping. Do not write to candidate devices. | Oracle DBA, Linux, storage teams
Final evidence shows a mismatch or FinalStateCompliant=False | Treat as blocking. Keep both VMs powered off, export live inventory, compare with the Phase I manifest, and correct only after peer review. | Migration lead

## Rollback Plan
Rollback Procedure
Step | Action | Completed
Rollback Before Migration
R1.1 | Keep both source VMs powered off.
R1.2 | Use the Phase I manifest and controlled procedure to reattach each original shared VMDK to the source Secondary at the original SCSI node, with independent_persistent and sharingMultiWriter.
R1.3 | Explicitly restore sharingMultiWriter and the original disk mode on every reattached Secondary device.
R1.4 | Verify Primary shared disks were never detached or changed and remain Multi-writer.
R1.5 | Run a complete manifest comparison. Do not power on until source configuration matches the pre-change state.
Rollback After Migration but Before Power-On
R2.1 | Keep both destination VMs powered off. Preserve Phase I and Phase II run folders, task IDs, request artifacts, applied-change evidence, final mappings, and validation results.
R2.2 | Do not delete destination VMDKs or attempt ad hoc disk conversion.
R2.3 | If the approved rollback requires return to source, follow the selected migration product or platform rollback procedure and confirm authoritative VM registrations and VMDK ownership.
R2.4 | Reconstruct the source Secondary shared-disk attachments from the manifest if required.
R2.5 | Validate the full source configuration before controlled power-on.
Rollback After Any VM Has Powered On
R3.1 | Oracle DBA stops application traffic and database/cluster services using the approved emergency procedure.
R3.2 | Shut down Secondary first and Primary second unless theDB incident lead directs otherwise.
R3.3 | EngageDB, storage, virtualization, and change leadership before moving or reattaching shared storage.
R3.4 | Use application-consistent backup recovery only through the approved recovery plan. VMware snapshots are not the rollback authority for independent-persistent shared disks.
R3.5 | Record the rollback outcome and completeDB integrity validation before returning service.

## Timeline & Contacts
Timeline, Hold Points, and Contact Information
Phase / Role | Estimated Time | Owner | Notes
Phase 1: Discovery, manifest, and controlled detach | 30-60 minutes | Cloud administrator | Complete before outage where possible; rerun live validation before detach
Phase 2:DB shutdown | 15-30 minutes | Oracle DBA | DBA-controlled
Phase 3: VM shutdown and detach | 15-30 minutes | Cloud administrator | Secondary shutdown first; detach secondary shared disks only
Phase 4: Cold migration | Environment dependent | Cloud administrator | Primary first; hold point before Secondary
Phase 5: Primary preparation and Secondary reconstruction | 30-60 minutes | Cloud administrator | Restore missing Primary Multi-writer when required, reattach existing VMDKs, and publish final compliance evidence
Phase 6: Controlled power-on | 20-45 minutes | Cloud administrator /DB DBA | Primary first; Secondary only after approval
Phase 7:DB validation | 30-90 minutes | Oracle DBA / application owner | Includes business validation
Rollback reserve | Defined by change record | Migration lead | Do not consume without change-lead approval
Contacts
Migration Lead
Cloud / VMware Administrator
Oracle DBA
Linux Administrator
Storage Administrator
Network Administrator
Backup / Recovery Administrator
Change Manager
Business / Application Owner

## References
Broadcom References and Design Notes
Reference | URL | Use in Runbook
Broadcom KB 390585 - Storage migration of virtual machines with Shared VMDKs | https://knowledge.broadcom.com/external/article/390585/storage-migration-of-virtual-machines-wi.html | Cold migration, detach shared disks from secondary nodes, preserve SCSI controller/unit mapping, primary-first power-on.
Broadcom KB 313527 - Multi-writer flag | https://knowledge.broadcom.com/external/article/313527/enabling-or-disabling-simultaneous-write.html | Multi-writer purpose, application-level coordination, and caution regarding data corruption.
Broadcom KB 327037 - Using Oracle RAC on a vSAN Datastore | https://knowledge.broadcom.com/external/article/327037/using-oracle-rac-on-a-vsan-datastore.html | Oracle RAC multi-writer design and distinction from clustered VMDK.
Broadcom KB 383195 - Multi-writer disks and snapshots | https://knowledge.broadcom.com/external/article/383195/understanding-multiwriter-disks-and-thei.html | Snapshot and CBT limitations for multi-writer and independent-persistent disks.
Broadcom KB 344959 - Cross-vCenter migration requirements | https://knowledge.broadcom.com/external/article/344959/cross-vcenter-migration-and-clone-requir.html | Cross-vCenter migration prerequisites and supported approaches.
Broadcom KB 344918 - Cold migration connectivity | https://knowledge.broadcom.com/external/article/344918/cold-migrations-within-the-same-or-diffe.html | NFC/provisioning path and TCP 902 troubleshooting considerations.
Broadcom KB 323382 - Multi-writer power-on and CBT | https://knowledge.broadcom.com/external/article/323382/powering-on-a-vm-configured-with-the-mul.html | CBT-related lock and power-on risks.
Design decision | N/A | Primary shared disks remain attached. Phase II detects and restores Multi-writer if cross-vCenter migration removes it. Only Secondary shared disks are detached and later reconstructed; backing files are never deleted.
Phase I Final v1.2.0 | N/A | Authoritative source discovery, evidence export, controlled Secondary detach, and post-change validation utility.
Phase II Final v2.2.0 | N/A | Authoritative destination evidence verification, Primary Multi-writer restoration, Secondary reconstruction, and final compliance validation utility.